## Sprint Backlog
Sprint 1 (Weeks 5-6)
Sprint Backlog ID | User Story | Priority
SPR-01_PBL-01 | As a Client, I want to register an account, so that I can request legal services. | High
SPR-01_PBL-02 | As a Partner, I want to register law firm staff accounts, so that legal and admin employees get role-appropriate access. | High
SPR-01_PBL-03 | As any user, I want to log in, land on my role's home page, view my profile, change my password and log out, so that my account stays secure and I can use the features of my role. | High
SPR-01_PBL-04 | As a Client, I want to request a consultation with legal issue details and track its status and consultation meeting, so that the firm can evaluate my legal matter and I know where it stands. | High
SPR-01_PBL-05 | As a Partner, I want to search the database for clients, staff members, and contacts, so that I can perform a manual conflict-of-interest check. | High
SPR-01_PBL-06 | As a Partner, I want to approve and assign an Associate and Paralegal to a consultation request, or reject it, so that accepted matters are routed to the right legal staff. | High
SPR-01_PBL-07 | As an Associate or Paralegal, I want to schedule a consultation meeting for my assigned consultations, so that the Associate can meet the client to discuss the matter and decide whether to take it on. | High
SPR-01_PBL-08 | As an Associate, I want to accept or reject a consultation request after the meeting, so that only matters the firm can take on become cases. | High
SPR-01_PBL-09 | As an Associate, I want to open an active Case Workspace from an accepted consultation, so that case execution can begin. | High
Sprint 2 (Weeks 7-8)
Sprint Backlog ID | User Story | Priority
SPR-02_PBL-10 | As a Client, I want to upload evidence files to my case's staging folder and follow the case, its documents and its scheduled events, so that my lawyers can review supporting legal documents and I know where my matter stands. | High
SPR-02_PBL-11 | As an Associate or Paralegal, I want to review staged client documents and accept or reject them into the case workspace, so that legal documents are securely stored. | High
SPR-02_PBL-12 | As an Associate or Paralegal, I want to add and maintain a scheduling task to book calendar dates for site visits, negotiation sessions and client briefings, so that appointments are tracked. | High
SPR-02_PBL-13 | As an Associate or Paralegal, I want to add and maintain a documenting task, so that the documents produced for each piece of case work are recorded with it. | High
SPR-02_PBL-14 | As an Associate or Paralegal, I want to add and maintain a billing task to log case work and court appearance charges, so that case work is recorded for invoicing. | High
SPR-02_PBL-15 | As an Associate or Paralegal, I want to add and maintain contact and witness details in the case workspace, so that key contact information is organized for the case. | High
Sprint 3 (Weeks 9-10)
Sprint Backlog ID | User Story | Priority
SPR-03_PBL-16 | As a Client, I want to top up my trust account online and review my transaction history, so that I have funds available to settle legal invoices. | High
SPR-03_PBL-17 | As a Finance Officer, I want to view unbilled activity charge logs on a case's finance dashboard, so that I can audit pending legal charges before compiling invoices. | High
SPR-03_PBL-18 | As a Finance Officer, I want to compile unbilled charges into an itemized invoice and debit the client's trust account, so that invoices are marked PAID. | High
SPR-03_PBL-19 | As a Finance Officer, I want to process a cash withdrawal from a client's trust account and review the client's transaction history, so that funds can be returned to the client in person. | High
SPR-03_PBL-20 | As a Partner, I want to edit my own profile details, so that my contact information stays current. | Medium
SPR-03_PBL-21 | As a Partner, I want to manage every staff and client account, so that access can be corrected or revoked when needed. | Medium
SPR-03_PBL-22 | As a Client, I want to update or delete a consultation request while it is still pending, so that I can correct or cancel it before it is reviewed. | Medium
SPR-03_PBL-23 | As an Associate or Paralegal, I want to rename and delete the documents in a case, so that the case file stays accurate and complete. | Medium
SPR-03_PBL-24 | As an Associate or Paralegal, I want to view, reschedule, cancel or mark a scheduled event as complete, so that the calendar stays accurate as circumstances change. | Medium
SPR-03_PBL-25 | As a Finance Officer, I want to edit disputed pending charges, void incorrect invoices, and refund paid charges, so that billing errors can be corrected while the case is open. | Medium
SPR-03_PBL-26 | As an Associate, I want to close an active case with a final resolution status, so that completed cases are officially closed once all of their billing is settled. | Medium
Sprint 4 (Weeks 11-12)
Sprint Backlog ID | User Story | Priority
SPR-04_PBL-27 | As a Partner, I want to reassign the Associate or Paralegal on a consultation before its case is opened or on an open case, so that staffing can be corrected after the fact. | Medium
SPR-04_PBL-28 | As a Client Relations Officer, I want to register walk-in clients at the front desk, so that physical visitors can request legal services. | Low
SPR-04_PBL-29 | As a Client Relations Officer, I want to request consultations for walk-in clients and follow them and their scheduled consultation meetings, so that a Partner can perform a conflict check. | Low
SPR-04_PBL-30 | As a Client Relations Officer, I want to manage client accounts, so that the Partner isn't bothered with basic client account administration. | Low
SPR-04_PBL-31 | As a Client Relations Officer, I want to update or delete a consultation request, so that I can correct or cancel it on behalf of a walk-in client. | Low
SPR-04_PBL-32 | As a Finance Officer, I want to top up a client's trust account with in-person cash, so that a walk-in client's balance increases. | Low
SPR-04_PBL-33 | As a Partner, I want to view analytics and firm-wide records, so that I can monitor how the firm is performing. | Low