## Product Backlog
Product Backlog ID | User Story ID | User Story | Priority | Sprint | Status | Owner | Module
PBL-01 | UST-01 | As a Client, I want to register an account, so that I can request legal services. | High | Sprint 1 (Weeks 5-6) | Done | Sameera H.M.D. | Document Management
PBL-02 | UST-06 | As a Partner, I want to register law firm staff accounts, so that legal and admin employees get role-appropriate access. | High | Sprint 1 (Weeks 5-6) | Done | Jayasundara R.H. | Consultation Management
PBL-03 | UST-33 | As any user, I want to log in, land on my role's home page, view my profile, change my password and log out, so that my account stays secure and I can use the features of my role. | High | Sprint 1 (Weeks 5-6) | Done | Bandaranayake B.M.S.P. | Case Management
PBL-04 | UST-02 | As a Client, I want to submit a consultation request with legal issue details and track its status and consultation meeting, so that the firm can evaluate my legal matter and I know where it stands. | High | Sprint 1 (Weeks 5-6) | Done | Dunuthilaka D.M.S.T.B. | Finance Management
PBL-05 | UST-07 | As a Partner, I want to search the database for clients, staff members, and contacts, so that I can perform a manual conflict-of-interest check. | High | Sprint 1 (Weeks 5-6) | Done | Perera M.I.B. | User Management
PBL-06 | UST-08 | As a Partner, I want to approve and assign an Associate and Paralegal to a consultation request, or reject it, so that accepted matters are routed to the right legal staff. | High | Sprint 1 (Weeks 5-6) | Done | Mahaliyadda S.S. | Scheduling Management
PBL-07 | UST-16 | As an Associate or Paralegal, I want to schedule a consultation meeting for my assigned consultations, so that the Associate can meet the client to discuss the matter and decide whether to take it on. | High | Sprint 1 (Weeks 5-6) | Done
PBL-08 | UST-13 | As an Associate, I want to accept or reject a consultation request after the meeting, so that only matters the firm can take on become cases. | High | Sprint 1 (Weeks 5-6) | Done
PBL-09 | UST-14 | As an Associate, I want to open an active Case Workspace from an accepted consultation, so that case execution can begin. | High | Sprint 1 (Weeks 5-6) | Done
PBL-10 | UST-03 | As a Client, I want to upload evidence files to my case's staging folder and follow the case, its documents and its scheduled events, so that my lawyers can review supporting legal documents and I know where my matter stands. | High | Sprint 2 (Weeks 7-8) | Done
PBL-11 | UST-17 | As an Associate or Paralegal, I want to review staged client documents and accept or reject them into the case workspace, so that legal documents are securely stored. | High | Sprint 2 (Weeks 7-8) | Done
PBL-12 | UST-18 | As an Associate or Paralegal, I want to add and maintain a scheduling task to book calendar dates for site visits, negotiation sessions and client briefings, so that appointments are tracked. | High | Sprint 2 (Weeks 7-8) | Done
PBL-13 | UST-19 | As an Associate or Paralegal, I want to add and maintain a documenting task, so that the documents produced for each piece of case work are recorded with it. | High | Sprint 2 (Weeks 7-8) | Done
PBL-14 | UST-20 | As an Associate or Paralegal, I want to add and maintain a billing task to log case work and court appearance charges, so that case work is recorded for invoicing. | High | Sprint 2 (Weeks 7-8) | Done
PBL-15 | UST-21 | As an Associate or Paralegal, I want to add and maintain contact and witness details in the case workspace, so that key contact information is organized for the case. | High | Sprint 2 (Weeks 7-8) | Done
PBL-16 | UST-04 | As a Client, I want to top up my trust account online and review my transaction history, so that I have funds available to settle legal invoices. | High | Sprint 3 (Weeks 9-10) | Done
PBL-17 | UST-28 | As a Finance Officer, I want to view unbilled activity charge logs on a case's finance dashboard, so that I can audit pending legal charges before compiling invoices. | High | Sprint 3 (Weeks 9-10) | Done
PBL-18 | UST-29 | As a Finance Officer, I want to compile unbilled charges into an itemized invoice and debit the client's trust account, so that invoices are marked PAID. | High | Sprint 3 (Weeks 9-10) | Done
PBL-19 | UST-30 | As a Finance Officer, I want to process a cash withdrawal from a client's trust account and review the client's transaction history, so that funds can be returned to the client in person. | High | Sprint 3 (Weeks 9-10) | Done
PBL-20 | UST-09 | As a Partner, I want to edit my own profile details, so that my contact information stays current. | Medium | Sprint 3 (Weeks 9-10) | Done
PBL-21 | UST-10 | As a Partner, I want to manage every staff and client account, so that access can be corrected or revoked when needed. | Medium | Sprint 3 (Weeks 9-10) | Done
PBL-22 | UST-05 | As a Client, I want to update or delete a consultation request while it is still pending, so that I can correct or cancel it before it is reviewed. | Medium | Sprint 3 (Weeks 9-10) | Done
PBL-23 | UST-22 | As an Associate or Paralegal, I want to rename and delete the documents in a case, so that the case file stays accurate and complete. | Medium | Sprint 3 (Weeks 9-10) | Done
PBL-24 | UST-23 | As an Associate or Paralegal, I want to view, reschedule, cancel or mark a scheduled event as complete, so that the calendar stays accurate as circumstances change. | Medium | Sprint 3 (Weeks 9-10) | Done
PBL-25 | UST-31 | As a Finance Officer, I want to edit disputed pending charges, void incorrect invoices, and refund paid charges, so that billing errors can be corrected at any stage. | Medium | Sprint 3 (Weeks 9-10) | Done
PBL-26 | UST-15 | As an Associate, I want to close an active case with a final resolution status, so that completed cases are officially closed. | Medium | Sprint 3 (Weeks 9-10) | Done
PBL-27 | UST-11 | As a Partner, I want to reassign the Associate or Paralegal on a consultation or case, so that staffing can be corrected after the fact. | Medium | Sprint 4 (Weeks 11-12) | Done
PBL-28 | UST-24 | As a Client Relations Officer, I want to register walk-in clients at the front desk, so that physical visitors can request legal services. | Low | Sprint 4 (Weeks 11-12) | Done
PBL-29 | UST-25 | As a Client Relations Officer, I want to submit walk-in clients' consultation requests and follow them and their scheduled consultation meetings, so that a Partner can perform a conflict check. | Low | Sprint 4 (Weeks 11-12) | Done
PBL-30 | UST-26 | As a Client Relations Officer, I want to manage client accounts, so that the Partner isn't bothered with basic client account administration. | Low | Sprint 4 (Weeks 11-12) | Done
PBL-31 | UST-27 | As a Client Relations Officer, I want to update or delete a consultation request, so that I can correct or cancel it on behalf of a walk-in client. | Low | Sprint 4 (Weeks 11-12) | Done
PBL-32 | UST-32 | As a Finance Officer, I want to top up a client's trust account with in-person cash, so that a walk-in client's balance increases. | Low | Sprint 4 (Weeks 11-12) | Done
PBL-33 | UST-12 | As a Partner, I want to view analytics and firm-wide records, so that I can monitor how the firm is performing. | Low | Sprint 4 (Weeks 11-12) | Done